## Sheet1
Phase | RAI Focus Area | Checklist Item | Owner | Status | Evidence / Notes
Initiation | Ethical Governance | Confirm project aligns with org’s Responsible AI policy or ethics charter | PM
Initiation | Stakeholder Inclusion | Identify cross-functional stakeholders (Legal, Ethics, Data, Sustainability) | PM
Initiation | Value Alignment | Ensure business case defines intended benefit for people and society | Sponsor
Planning | Data Governance | Validate data sources for consent, privacy, representativeness | Data Owner
Planning | Risk Management | Add bias, explainability, and sustainability risks to the risk register | PM
Planning | Transparency | Define auditability plan for models and datasets | Tech Lead
Execution | Fairness & Bias | Apply fairness testing tools (e.g., Azure RAI Dashboard, AIF360) | ML Engineer
Execution | Human Oversight | Define when human intervention is required for critical decisions | PM / Product Owner
Execution | Sustainability | Track model compute usage and energy footprint | Tech Lead
Monitoring & Control | Accountability | Review RAI KPIs in steering committee reports | PM
Monitoring & Control | Compliance | Conduct periodic RAI compliance reviews | PMO
Closure | Transparency | Publish AI system card describing purpose, limits, and testing | PM / Comm
Closure | Lessons Learned | Capture what worked / failed in RAI integration | PM